## Sheet1
CEP Portal
Task | Deadline
Add functionality for the supervisor to add coding questions as well 1. Node js backend for question adding 2. Frontend for adding code question 3. API service integration for coding question | 2019-10-11
Automatic evaluation of the questions. The marks should have a certain benchmark that needs to be crossed in order to qualify the test. 1. Automatic calculation of the marks to be done. 2. The score should be reflected in frontend for the candidate | 2019-10-18
After evaluation by the supervisor, there should be a provision to add a feedback by the supervisor to the candidate. 1. At the end of the evaluation, the system should ask for feedback of the supervisor. This has to be optional 2. The feedback should be visible to the candidate as well as supervisor | 2019-10-25
Test scores should be visible to the supervisor as well 1. When the test evaluation is completed, the corresponding score should be updated in the database. This score should be reflected for candidate as well as supervisor | 2019-11-01
Separate menu for the supervisor to view the courses that are already evaluated 1. Add a new option in role_menu for supervior role 2. Add component, view and services in frontend for listing out all the evaluated tests 3. Backend API fro listing out all the evaluated courses | 2019-11-08
Addition of search functionality in every listing page 1. Addition of search functionality on every listing page - Technology, Category, Users, Courses 2. Frontend for search functionality 3. Backend for search functionality | 2019-11-15
Timer to be added in the exam. Timer should start as soon as the first question is displayed to the candidate. 1. Add timer to the exam frontend 2. Update the timer value in the database 3. Backend for the timer updation - With every question, the timer will be updated | 2019-11-22
Start the exam from where the exam was left 1. When attempting the exam, check if the exam is already attempted. If yes, load the question next to previously attempted. 2. Backend for updating the question status every time the question is answered | 2019-11-29